## Slide 1: Agenda
Administrative
Introduction to Agile Project Management
Syllabus
Poll Everywhere

## Slide 2: Poll Everywhere
Detailed instructions available via eLearning
Must create a registered account
Cost $14
Respond via browser
www.pollev.com/thouin

## Slide 3: What is a Project?
Project Defined
A complex, nonroutine, one-time effort limited by time, budget, resources, and performance specifications designed to meet customer needs.
Major Characteristics of a Project
Has an established objective
Has a defined life span with a beginning and an end
Requires across-the-organizational participation
Involves doing something never been done before
Has specific time, cost, and performance requirements

## Slide 4: Project Success
Under what conditions is a project deemed to have been successful?

## Slide 5: Project Performance Varies Greatly
Notes: Part of a survey of 5,400 IT projects with budgets greater than $15 million
“On average, large IT projects run 45 percent over budget and 7 percent over time, while delivering 56 percent less value than predicted. Software projects run the highest risk of cost and schedule overruns1.” http://www.mckinsey.com/insights/business_technology/delivering_large-scale_it_projects_on_time_on_budget_and_on_value

## Slide 6: Causes of Cost Overruns

## Slide 7: Project Success Factors
Notes: How do we define project success?

## Slide 8: What is Project Management?
Project management is the application of knowledge, skills, tools and techniques to project activities to meet the project requirements
Source: PMBOK

## Slide 9: Business Alignment
Organizational Mission, Vision, Core Values, Objectives
  Organizations create strategic plans to achieve objectives
  Portfolio, program and project management ensures alignment with strategic plan
Portfolio Management
  Collection of programs that are grouped together to facility effective management and alignment with strategic plan (e.g. Microsoft Business Solutions)
Program Management
    Collection of projects that are grouped together to facility effective management and alignment with strategic plan (e.g. Microsoft Office 365)
Project Management
  Focus on achieving project objectives (e.g. Microsoft Word 365)

## Slide 10: Project Success
At or under budget
At or ahead of schedule
All required features and benefits
Stakeholder satisfaction
  Importance of conversations with stakeholders
Achieves desired outcomes
Other?

## Slide 11: Software Project Management
Project Management
  PMI PMBOK Fifth Edition
  5 Process Groups, 10 Knowledge Areas, 47 Processes
Project Delivery
  Systems Development Lifecycles (SDLC)
    Waterfall
    Iterative
    Agile

## Slide 12: 15th Annual State of Agile Survey
Source: Digital.ai www.stateofagile.com
Notes: 40,000 respondents

## Slide 13: 15th Annual State of Agile Survey
Source: Digital.ai www.stateofagile.com
Notes: 40,000 respondents

## Slide 14: 15th Annual State of Agile Survey
Source: Digital.al www.stateofagile.com

## Slide 15: 15th Annual State of Agile Survey
Source: Digital.al www.stateofagile.com

## Slide 16: 15th Annual State of Agile Survey
Source: Digital.al www.stateofagile.com

## Slide 18: Understanding the Project Lifecycle
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams
Planned – PMI PMBOK
Adaptive - Scrum/Agile

## Slide 19: Project Management - Process Groups
Initiating
Planning
Executing
Monitoring/Controlling
Closing
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams

## Slide 20: Project Management Process Groups
Stage (Process Group) | Main Goal | Main Output
Initiating | Authorize the Project | Project charter and stakeholder register
Planning | Plan and schedule the work to perform the project | Project management plan that contains subsidiary plans, such as scope management plan and schedule management plan
Executing | Perform the project work | Project deliverables: product, service, result
Monitoring and Controlling | Monitor the progress of the project to identify the variance from the plan and to correct it | Change requests and recommendations for preventive and corrective action
Closing | Close the project formally | Product acceptance and contract closure
PMP in Depth

## Slide 21: Big Picture of Project Management
Stakeholder Management
Notes: 5 Process Groups, 10 Knowledge Areas, 47 Processes

## Slide 22: The Triple Constraint (The Iron Triangle)
Quality Software Project Management
PMP in Depth

## Slide 23: Project Delivery - Waterfall SDLC
Requirements
Design
Develop
Test
Implement

## Slide 24: Project Delivery – Scrum SDLC

## Slide 25: Scrum Sprint
Source: Essential Scrum by Kenneth S. Rubin p. 17
Notes: Agile software development emphasizes agility and the ability to adapt to changing conditions
  Time boxed deliverables
  Limited up-front planning, frequent product deliverables, limited documentation, and quick daily meetings with team and customers

## Slide 26: The Project Manager
Person responsible for achieving project objectives
  Different from a functional manager
  Different from a Scrum Master
  Must be able to effectively use and apply project management principles
Interpersonal skills
  Leadership Political and cultural awareness
  Team building Negotiation
  Motivation Trust building
  Communication Conflict Management
  Influencing Coaching
  Decision making
PMP in Depth

## Slide 27: Scrum
Scrum Master
  Helps everyone involved understand Scrum values, principles and practices
  Coach, servant leader, process authority, impediment remover, influencer
Product Owner
  Single point of product leadership
Developers
  Perform the work required to build the software product

## Slide 28: Exercise
Quantum Bank

## Slide 29: Group Project Signup
Group Projects
Microsoft Project Professional 2019
Poll Everywhere