## Slide 1: Agenda
Product Backlog Grooming
Estimation
Exam Reminder

## Slide 2: Product Backlog
Central Component of the Scrum Process
  Contains all desired product functionality
Initially developed as part of user story workshops done at the beginning of the project
  User stories become product backlog items
Product backlog items may be features, defects, technical work, or knowledge acquisition
Product Backlog Example
  Development of Scrum Alliance Website

## Slide 3: Scrum Flow
Project Charter
  Business case, high level project scope, major milestones, product vision
User Story Development
  Story writing workshops
Product Roadmap and Release Plan
  Product backlog grooming
Sprint Execution
  Multiple iterations
Release Software
  Deploy software to operational environment
Project Close

## Slide 4: Product Backlog Grooming
The process of elaborating on and prioritizing product backlog items
  The product backlog is refined over time
Product backlog contains user stories at varying degrees of detail (epic, theme, story)
  Lower priority items have fewer details
  Progressive elaboration adds detail as we move forward with the process
Scrum is an agile process so we embrace and expect changes
    Changes may occur during sprint planning or any other phase of the scrum process
    Sprint backlog does not change once a sprint is started

## Slide 5: Product Backlog Grooming
Source: Essential Scrum

## Slide 6: Estimation

## Slide 7: What is estimation?
Estimates set expectations about the time required to complete the software
  Stakeholders
  Team
  Organization’s management
If expectations are not realistic from the beginning of the project, the stakeholders will not trust the team or the project manager
  “Unrealistic expectations based on inaccurate estimates are the single largest cause of IT project failure” (Futrell, Shafer and Shaefer, QSPM as quoted in Nelson and Morris MISQE 2014)

## Slide 8: Estimation Techniques
Three Point Estimation
Analogous Estimation
Planning Poker

## Slide 9: Three Point Estimation
Each Project Activity or PBI is Given Three Estimates
  Most Likely Scenario
  Optimistic Scenario
  Pessimistic Scenario
Bottom-up approach where project delivery dates are calculated by rolling-up individual activity estimates
Indicates the level of uncertainty for each activity
Requires additional effort to provide 3 estimates for each activity
PERT
  te = (ntm + to + tp)/(n+2) where tm= most likely estimate, to= optimistic estimate, and tp = pessimistic estimate

## Slide 10: Analogous Estimation
May be top-down or bottom-up
Find similar projects and/or activities and see how long they took
May require minimal effort and can be a good sanity check

## Slide 11: Planning Poker
Common scrum technique for estimating prioritized list of Product Backlog Items
  Estimate in Story Points or Ideal Days
Scrum Backlog Typically Contains
  Features
  Bugs
  Technical Work
  Knowledge Acquisition
Source: http://www.mountaingoatsoftware.com/agile/scrum/product-backlog

## Slide 12: Planning Poker
Scrum Technique
  Very similar to Delphi Approach
Scrum team estimates PBIs using a set of playing cards
  Cards have numbers corresponding to size of estimate
Numbers are typically are not sequential
  0, ½, 1, 2, 3, 5, 8, 13, 20, 40, 100
Relative Measure of Size
  Tiny = ½, Small = 1, 2, 3, Medium = 5, 8, 13, Large = 20, 40, Epic = 100
Special Cards
  Infinity, ?, pi

## Slide 13: Planning Poker Protocol
The product owner selects a PBI to be estimated and reads the item to the team
Development team members discuss the item and ask clarifying questions to the product owner, who answers the questions
Each estimator privately selects a card representing his estimate
Once each estimator has made a private selection, all private estimates are simultaneously exposed to all estimators
If everyone selects the same card, we have consensus, and that consensus number becomes the PBI estimate
If the estimates are not the same, the team members engage in a focused discussion to expose assumptions and misunderstandings. Typically, we start by asking the high and low estimators to explain or justify their estimates.
After the discussion, we return to step 3 and repeat until consensus is reached.

## Slide 14: Planning Poker
Agile Estimating and Planning
PlanningPoker.com