## Slide 1: Product Planning with Scrum

## Slide 2: The Project Lifecycle
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams
Planned – PMBOK
Adaptive - Scrum/Agile

## Slide 3: Scrum Flow
Project Charter
  Business case, high level project scope, major milestones, product vision
User Story Development
  Story writing workshops
Product Roadmap and Release Plan
  Product backlog grooming
Sprint Execution
  Multiple iterations
Release Software
  Deploy software to operational environment
Project Close

## Slide 4: Product Vision
Clear, concise description of product and product value statement

## Slide 5: A “Vision” contains two major components
Envisioned future
  Contains Core Values and Purpose
  10 – 30 year audacious goal with a vivid description
Core values and vision rarely change
Building Your Company’s Vision, Collins and Porras, 1996
Notes: Walt Disney
  No cynicism
  Nurturing and promulgation of wholesome values
  Creativity, dreams, and imagination
  Fanatical attention to consistency and detail
  Preservation and control of the Disney magic

## Slide 6: Putting it All Together: Sony in the 1950s
Core Ideology
Core Values
  Elevation of the Japanese culture and national status
  Being a pioneer – not following others; doing the impossible
  Encouraging individual ability and creativity
Core Purpose
  To experience the sheer joy of innovation and the application of technology for the benefit and pleasure of the general public.
Envisioned Future
BHAG
  Become the company most known for changing the worldwide poor-quality image of Japanese products
  Vivid Description
  We will create products that become pervasive around the world…We will b the first Japanese company to go into the U.S. market and distribute directly… We will succeed with innovations that U.S. companies have failed at – such as the transistor radio… Fifty years from now, our brand name will be as well known as any in the world
Building Your Company’s Vision, Collins and Porras, 1996

## Slide 7: Discussion
Provide an example of software product that has a clear, well defined vision

## Slide 8: User Stories and Product Backlog
Prioritized list of product features
  Product Backlog Items (PBI)
  Size of PBIs are typically measured in story points

## Slide 9: Product Roadmap
Release schedule for the product along with major project milestones (e.g. minimum required functionality, market events, architecture, key features, etc.)

## Slide 10: Velocity
Velocity is the amount of work completed each sprint
  Typically measured in story points
Essential component of product planning
  It tells one how much work can be completed each sprint
May be used as a diagnostic
  Track velocity over time for each sprint and look for differences

## Slide 11: Release Planning

## Slide 12: (Source: Essential Scrum, p. 310)

## Slide 13: Using Velocity to Plan Release Schedule
(Source: Essential Scrum, p. 134)

## Slide 14: Class Exercise
Assume MVP contains 410 story points of work. How long will it take to deliver MVP if velocity is 18 story points per sprint and each sprint is two weeks in duration?

## Slide 15: Sprint Planning and Sprint Execution

## Slide 16: Sprint Planning
Decide which product backlog items to work on in a given sprint
  Requires an understanding of capacity/velocity
  Serves as a feasibility check
Output is sprint backlog containing detailed tasks for each PBI
  Useful for communication and tracking

## Slide 17: Sprint Backlog
(Source: Essential Scrum, p. 345)

## Slide 18: Using Velocity as a Diagnostic During Sprint Execution
(Source: Essential Scrum, p. 359)

## Slide 19
Total hours of all user stories at the beginning of the sprint
Remaining hours of all user stories at the end of each day
Cumulative total of business value points
earned to date
Cumulative total of user story points
earned to date

## Slide 20: Using Velocity as a Diagnostic
Useful for comparing output of multiple sprints
Useful for release planning
Should not be used to assess performance
Difficult to use between Scrum teams

## Slide 21: Release Planning Software Tools
Version One
Scaled Agile Framework
Jira Software
Azure DevOps