## Sheet1
BAC (Budget at completion) | 6000
EV | 3750
Work completed | 2.5 | sides completed
Total work required | 4 | sides required
Time passed | 72 | hours
Total scheduled time | 96 | hours
Planned Value(PV) | 4500
Actual cost (AC) | 4250
Cost variance (CV) | -500
Schedule Variance (SV) | -750
Estimated Cost at Completion (ECAC) | 6800
Original Time | 96 | hours
Estimated Time at Completion (ETAC) | 115.2
Cost Variance at Completion | -800
EV at completion
Schedule Variance at Completion