## Slide 1: MIS 6360 Agile Project Management
Project Initiation and the Project Charter

## Slide 2: Agenda
Administrative
  Poll Everywhere
Initiating the Project
The Project Charter
Stakeholder Management

## Slide 3: Initiating the Project

## Slide 4: Understanding the Project Lifecycle
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams
Planned – PMBOK
Adaptive - Scrum/Agile

## Slide 5: Initiating the Project
Business Mission, Vision and Strategy
Business Goals and Objectives
Business Need/ Opportunity
Business Case
Project Charter

## Slide 6: Identifying Business Needs and Opportunities
Business Requirements
  Legal or Regulatory
Opportunities
  Customer Requests
  Market Demand
  New Technology
Problems
  Address specific Problem Areas

## Slide 7: Project Selection Methods
Scoring models using weighted criteria
Cost Benefit Analysis
Expert Judgment

## Slide 8: Scoring Models
Source: Adapted from Project Management by Gray and Larson
 | Strategic Fit | Urgency | Improve Customer Loyalty | ROI of 18% plus | Regulatory Compliance | Weighted Total
Weight | 4.0 | 2.0 | 1.0 | 5.0 | 10.0 | 
Project 1 | 8 | 2 | 6 | 5 | 0 | 67
Project 2 | 1 | 3 | 2 | 2 | 0 | 22
Project 3 | 1 | 1 | 1 | 1 | 10 | 112
. . . |  |  |  |  |  | 
Project n | 9 | 8 | 8 | 9 | 0 | 105

## Slide 9: Cost Benefit Analysis
Cost, Revenue, and Project Savings
  Can be hard to quantify value of intangibles

## Slide 10: IT Benefits
Tangible Benefits
  Increases in revenue
  Reduction in labor costs
  Reduction in supplies needed
  Reduction in maintenance costs
Intangible Benefits (Difficult to Measure and Quantify)
  Improvements in decision making
  Improvements in communication
  Improvements in compliance
  Improvements in collaboration

## Slide 11: IT Costs
Hardware
Software
Communication
Labor
Education and Training

## Slide 12: Project Identification Exercise
Identify a software development project that you think would be beneficial for UT Dallas to undertake. Provide a short 2 – 3 sentence description of the project highlighting the proposed value and benefits of the project.

## Slide 13: Project Selection Benefit Measurement
Return on Investment (ROI)
  Ignoring the time value of money, the percentage of profit from the project
  ROI = (Benefits – Costs) / Costs
Internal Rate of Return (IRR)
  Translates yearly cost/benefit amounts to an interest rate over the life of the project
  Excel IRR function
Net Present Value (NPV)
  The present value of future cash inflows (benefits) minus the present value of future cash outflows (costs)
  Excel NPV Function
  Present Value Discount Factor = 1/(1 + r)^t where r = interest rate and t = time

## Slide 14: Exercise
Calculate the ROI, NPV, and IRR of the following project. Where appropriate, assume a 10% discount rate. Should you move forward with the project?
Year | Cost | Revenue
0 | 500,000 | 0
1 | 10,000 | 5,000
2 | 10,000 | 50,000
3 | 10,000 | 75,000
4 | 10,000 | 100,000
5 | 10,000 | 125,000
6 | 10,000 | 150,000
7 | 10,000 | 150,000
8 | 10,000 | 150,000
9 | 10,000 | 150,000
10 | 10,000 | 150,000

## Slide 15: Exercise
Calculate the ROI, NPV, and IRR of the following project. Where appropriate, assume a 10% discount rate. Should you move forward with the project?
Year | Cost | Revenue
0 | 1,000,000 | 0
1 | 100,000 | 50,000
2 | 100,000 | 100,000
3 | 100,000 | 200,000
4 | 100,000 | 300,000
5 | 100,000 | 350,000
6 | 100,000 | 400,000
7 | 100,000 | 450,000
8 | 100,000 | 500,000
9 | 100,000 | 550,000
10 | 100,000 | 600,000

## Slide 16: Exercise – Sensitivity Analysis
Conduct an interest rate sensitivity analysis for the following project by calculating the NPV for all discount rates between 2% and 18% in 1% increments. Should you move forward with the project?
Year | Cost | Revenue
0 | 1,000,000 | 0
1 | 100,000 | 50,000
2 | 100,000 | 100,000
3 | 100,000 | 200,000
4 | 100,000 | 300,000
5 | 100,000 | 350,000
6 | 100,000 | 400,000
7 | 100,000 | 450,000
8 | 100,000 | 500,000
9 | 100,000 | 550,000
10 | 100,000 | 600,000

## Slide 17: Project Selection Expert Judgment
Expert Judgment

## Slide 18: Developing the Project Charter

## Slide 19: Developing the Project Charter
Formally Authorizes the Project and Identifies a Project Manager
PMP in Depth: Project Management Professional Study Guide for PMP and CAPM Exams
Input
Business Case
Tools and Techniques
Expert Judgment
Output
Project Charter
Contract
Enterprise Environmental Factors
Organizational Process Assets
Statement of Work

## Slide 20: Output of Developing the Project Charter
Project purpose or justification
Measurable project objectives and related success criteria
High-level requirements
High-level project description
High-level risks
Summary milestone schedule
Summary budget
Project approval requirements
Assigned project manager
Name and authority of the sponsor

## Slide 21: Project Charter Templates
California Department of Technology Agile Project Charter
  California Project Management Methodology
  Not Perfect
Smart Sheet

## Slide 22: Exercise
For the project you previously identified, create a draft project charter covering the following items.
  Project Name
  High-level project description including the purpose of the project
  Success criteria including measurable project objectives
  High-level requirements
  Summary milestone schedule
  Summary budget
  Names of project sponsor, project manager, and product manager

## Slide 23: Identifying the Project Stakeholders

## Slide 24: Identifying Project Stakeholders
Project Manager
Project Management Office
Project Management Team
Project Team Members
Performing Organizations
Customer/user
Project Sponsor
Influencers

## Slide 25: Stakeholder Register
Document used to store information about stakeholders
  Identification – name, location, title, project role, contact information
  Assessment – list of how the stakeholder will react to different scenarios
  Classification – power/interest grid, power involvement/grid, involvement/impact grid, salience model

## Slide 26: Stakeholder Management
The approach developed to deal with the stakeholders in the best interests of the project
  How will individual stakeholders be managed?
  How ill groups of stakeholders be managed?

## Slide 27: Power/Interest Grid
Monitor Closely | Manage with maximum effort
Monitor | Keep informed
Interest Level
Authority Level
Stakeholder 9
Stakeholder 11
Stakeholder 10
Stakeholder 6
Stakeholder 4
Stakeholder 2
Stakeholder 8
Stakeholder 7
Stakeholder 3
Stakeholder 1
Stakeholder 5

## Slide 28: Exercise
Develop a stakeholder register for the project you identified in the previous exercise